## Report Page
<EVENT NAME> <location> <date, time> Bump and Run (runsheet)
DATE | START TIME | FINISH TIME | ACTION TYPE | ACTION | RESPONSIBLE PERSON | LOCATION
2015-05-25
2015-05-25 | 9:00 | 10:00 | BI | Sarah to email draft acknowledgements, guest list and run sheet to Host's office. | Event Coordinator | Events office
2015-05-26
2015-05-26 | 9:00 | 9:00 | BI | Sarah to refer to BOM website for an updated forecast. Forecast hotline: 07 3239 8700. Sarah to refer to Jules and Event Manager to discuss forecast. If extreme weather conditions predicted, Sarah to discuss options with Jules and Event Manager. Sarah to contact venue, equipment and AV supplier to discuss any changes to the ceremony. | SB | Events office
2015-05-27 | 12:00 | 15:00 | BI | Alicia/Zoe to print final name tags, reserved finalist, VIP seating and general reserved stickers. Please put one coloured dot on VIPs with reserved seating, another colour for sponsor presenters and a third colour for finalists. | S2, AS | Events office
2015-05-26 | 14:00 | 15:00 | BI | Staff briefing | SB | Events office
<DATE>
2015-05-27 | 7:00 | 7:00 | BI | Event Coordinator to refer to BOM website for an updated forecast. Event Coordinator to refer to Event Manager to discuss forecast. | Event Coordinator | Office
2015-05-27 | 8:00 | 16:00 | BI | Rental company arrive on site at venue to install marquee. | Rental co, Event Coordinator | Venue
2015-05-27 | 10:00 | 12:00 | BI | Event Coordinator to confirm seating plan based on latest RSVP list - reserved seating for VIPs. Provide updated copies to staff as required. | Event Coordinator | Office
2015-05-27 | 10:00 | 15:00 | BI | Event Coordinator to gather equipment list and tool kit | Event Coordinator, S2 | Office
2015-05-27 | 12:00 | 15:00 | BI | S2 to print final name tags, reserved finalist, VIP seating and general reserved stickers. | S2 | Office
<DATE>
2015-05-28 | 6:00 | 6:00 | BI | Event Coordinator refer to BOM website for an updated forecast. Refer to Operations Manual for detailed instructions. | Event Coordinator | Office
2015-05-28 | 8:00 | 14:00 | BI | Rental company on site to finalise bump in. S2 to meet. | Rental co, S2 | Venue
2015-05-28 | 9:00 | 9:30 | BI | Event Coordinator and S2 to head to venue to drop off equipment and check in with venue and oversee bump in. | Event Coordinator, S2 | Venue
2015-05-28 | 9:00 | 12:00 | BI | Event Coordinator and S2 to commence set up of the following throughout the morning: - Set up programs on chairs - BS6rs on stage and in foyer - Lectern signs - Certificate and announcement cards table - Reserved seating (refer to seating plan) - Registration area in foyer including name tags - Sponsor signage in foyer | Event Coordinator, S2 | Venue
2015-05-28 | 9:15 | 9:30 | BI | Event Coordinator checks the venue has been set up acorrding to brief. | Event Coordinator | Venue
2015-05-28 | 9:30 | 9:30 | BI | AV company arrive on site. Met and briefed by S2. | AV, S2 | Venue
2015-05-28 | 11:00 | 11:30 | BI | Event Coordinator to check in with catering team | Event Coordinator | Venue
2015-05-28 | 12:00 | 13:00 | BI | S2 to finalise set up of trophy and certificate table and check against master list and MC notes. Tables to be ready for rehearsal at 2.30pm | S2 | Venue
2015-05-28 | 13:00 | 13:00 | BI | Event Manager arrives on site | Event Manager | Venue
2015-05-28 | 13:30 | 14:30 | BI | S2 to set-up name tag table and double check all VIPs have coloured dots. S3 to assist once on site. | S2, S3 | Venue
2015-05-28 | 14:00 | 14:00 | BI | S3 arrives onsite. Please familiarise yourself with the venue facilities and your area upon arrival. | S3 | Venue
2015-05-28 | 14:00 | 14:00 | BI | Infrastructure/equipment install complete by Rental company. Rental company to depart site. | Rental co | Venue
2015-05-28 | 14:00 | 14:30 | BI | Event Coordinator to place reserved stickers on seats according to seating plan. | Event Coordinator | Venue
2015-05-28 | 14:30 | 14:30 | BI | AV co. to be ready for full event rehearsal. | AV co | Venue
2015-05-28 | 14:45 | 15:45 | BI | Full event rehearsal | All staff | Venue
2015-05-28 | 15:45 | 15:45 | BI | Flower delivery co arrives on site with flower delivery. Met and briefed by S2. | FCO, S2 | Venue
2015-05-28 | 16:00 | 17:00 | BI | All staff to assist with left over tasks. - programs on seats - name tag table set up - final annoucement card, certificates, trophies check - signage (bS6rs and directional signage) | Event Coordinator, S2, S3 | Venue
2015-05-28 | 16:30 | 16:30 | BI | S4 to set up video camera | S4 | Venue
2015-05-28 | 16:30 | 16:45 | BI | S2 to check in with catering to ensure ready to go for pre-ceremony drink service at 6 pm. | S2, catering | Venue
2015-05-28 | 16:45 | 16:45 | BI | MC arrives on site. Met and briefed by Event Manager. | Event Manager | Venue
2015-05-28 | 16:45 | 16:45 | BI | S7 and S8 arrive on site. | AS, GS | Venue
2015-05-28 | 17:00 | 17:00 | BI | Performer #1 arrives on site. Met and briefed by S2. Shown to foyer area for set up. | Event Coordinator, S2 | Venue
2015-05-28 | 17:00 | 17:00 | BI | Event Manager, S5 and S6 arrive on site. S5 and S6 to collect radios from staff room. | RR, MW, AH | Venue
2015-05-28 | 17:00 | 17:00 | BI | All EC staff to be on radios. Collect from Speaker's Dining Room (EC staff room) | All EC staff | Venue
2015-05-28 | 17:00 | 17:00 | BI | Performer #2 arrives on site for set up and sound check. Met and briefed by S2. | JW | Venue
2015-05-28 | 17:00 | 17:15 | BI | Finalist briefers and Event Coordinator to gather and discuss process in briefing finalists. | KG, GS, S2, Event Coordinator | Venue
2015-05-28 | 17:00 | 17:15 | BI | S7 and S9 to become familiar with name tag table, acknowledgements list, coloured dot system for VIPs and general guests name tags. | AS, SD | Venue
2015-05-28 | 17:00 | 17:15 | BI | Sound check with MC and AV. | MC, VD, Event Manager | Venue
2015-05-28 | 17:15 | 17:30 | BI | Performer #1 ready for sound check. S2 to monitor | S2 | Venue
2015-05-28 | 17:15 | 17:30 | BI | Performer #2 sets up and sound checks with AV. S2 to monitor. Sound check to be complete by 5.30pm. | CT, JW | Stage 2
2015-05-28 | 17:30 | 17:30 | BI | Performer #1 soundcheck complete. Break for 45 minutes. | S2 | Venue
2015-05-28 | 17:30 | 17:30 | BI | Event ready | All staff | Venue
2015-05-28 | 17:30 | 17:45 | BI | Finalists start arriving for briefing at 5.45pm. Staff in position at name tag table ready for early arrivals. Please brief finalists, collect any outstanding photo consent forms and show them to their reserved seating. Tick off each finalist team as they arrive. | All staff | Venue
2015-05-28 | 17:45 | 17:45 | BI | Photographer arrives on site. Met and briefed by S6. | AH | Venue
2015-05-28 | 17:45 | 17:45 | BI | Elders arrive on site. Met and briefed by Event Manager | Event Manager | Venue
2015-05-28 | 17:50 | 17:50 | BI | S2 to give caterers 10 minute cue to commence service | S2, Catering | Venue
2015-05-28 | 18:00 | 18:00 | RS | Guests begin to arrive and are given name tags. | AS, SH | Venue
2015-05-28 | 18:00 | 18:00 | RS | S2 to provide finalist arrival update to Event Coordinator | S2, Event Coordinator, Event Manager | Venue
2015-05-28 | 18:00 | 18:20 | RS | Performer #1 as guests arrive. S2 to monitor and provide cue to conclude peformance at approximately 6.20 pm. | BP, Event Coordinator | Venue
2015-05-28 | 18:00 | 18:25 | RS | Catering commence service of water, juice, tea and coffee. S2 to provide cue to commence. | S2, Catering | Venue
2015-05-28 | 18:15 | 18:15 | RS | Event Coordinator and Event Manager in position to meet and greet the Host. | Event Coordinator, RR | Venue
2015-05-28 | 18:20 | 18:20 | RS | S7/S9 to provide an updated Acknowledgements lists to MC and have one ready for Host. | AS, SH, GS | Venue
2015-05-28 | 18:20 | 18:25 | RS | Ushers and staff to begin ushering guests into marquee. | RN, Event Manager, JW | Venue
2015-05-28 | 18:20 | 18:25 | RS | Host arrives onsite and is met and briefed by Event Manager and provided with updated list of acknowledgements. Event Manager to escort Host to meet Performer and have photo and then onto marquee. | Event Coordinator, RR | Venue
2015-05-28 | 18:25 | 18:25 | RS | AV to turn off background music ready for official proceedings to commence. | JW, Event Coordinator | Venue
2015-05-28 | 18:25 | 18:25 | RS | S9 in position at trophy table, ready for ceremony to start. | KG, JW, Event Manager, Event Coordinator | Venue
2015-05-28 | 18:25 | 18:25 | RS | S2 to switch on video camera at the back of auditorium to record proceedings and return to position at side of stage. | JW | Venue
2015-05-28 | 18:25 | 18:25 | RS | Performer #1 representative and students to proceed to marquee for official proceedings. S2 to monitor and escort. | S2 | Venue
2015-05-28 | 18:30 | 18:30 | RS | Event Manager to provide cue to commence proceedings once Host is seated. | Event Coordinator | Venue
2015-05-28 | 18:30 | 18:30 | RS | OFFICIAL PROCEEDINGS COMMENCE MC to walk onto stage and commence proceedings. S2 to cue AV and lighting. S9 in position at trophy table. S7 and S9 to usher late guests. | All Staff | Venue
2015-05-28 | 18:30 | 18:32 | RS | MC welcomes guests and introduces acknowledgement of Traditional Owners. S8 near stage to assist speaker onto stage if required. | MC, VD, Event Coordinator, GS | Stage 1, left lectern
2015-05-28 | 18:32 | 18:35 | RS | Acknowledgement of Traditional Owners. | MC, BP | Stage 1, right lectern
2015-05-28 | 18:38 | 18:39 | RS | MC welcomes Host to stage. | AV, MC | Stage 1, left lectern
2015-05-28 | 18:39 | 18:43 | RS | Host address. Host remains on stage to present awards. | Host | Stage 1, right lectern
2015-05-28 | 18:40 | 18:40 | RS | S8 available to assist people on to stage if required. | S8, Event Manager | Stage 1, left and right side
2015-05-28 | 18:43 | 18:43 | RS | MC thanks Host and introduces Award category 1. | MC | Stage 1, left lectern
2015-05-28 | 18:43 | 18:53 | RS | Presentation of Award category 1 - MC introduces category and invites sponsor to stage. - Sponsor logo is displayed as MC reads bio about sponsor. - MC introduces category shortlist while sponsor is handed Highly Commended (HC) announcement card. - As MC introduces category shortlist, she will ask shortlisted entrants to stand, to be recognised by guests. - MC prompts sponsor to announce HC recipient - While HC recipient is walking to stage, music is played cued and Host is handed HC certificate by staff member. - Host presents certificate to HC recipient and poses for a photo with the recipient and sponsor. - Sponsor remains on stage while HC recipient departs stage and Host is handed winner announcement card. - MC invites Host to announce the winner. Host announces winner. - While winner is walking to stage, music is played, and S9 hands winner certificate to the Host and cheque to the sponsor. - Winner is presented with certificate and cheque, poses for a photo and is invited to make a short 2 minute speech from Host's lectern. - MC thanks winner for speech and prompts the winner and sponsor to depart stage and return to their seat. | MC, Sponsor, Host, Event Manager, Event Coordinator | MC - left lectern, Sponsor/Host - right lectern
2015-05-28 | 18:53 | 19:03 | RS | Presentation of Award category 2 - to follow the same process as the first category | MC, Sponsor, Host, Event Manager, Event Coordinator | MC - left lectern, Sponsor/Host - right lectern
2015-05-28 | 19:00 | 19:00 | RS | S9 and S7 can depart. | SH, AS | Venue
2015-05-28 | 19:00 | 19:15 | RS | S2 to check that catering staff and Performer #2 are on stand-by and ready to start cocktail function at 7.15 pm should official proceedings conclude earlier. Event Coordinator will advise when during second last category to check on timings. | Event Coordinator, S2 | Venue
2015-05-28 | 19:03 | 19:13 | RS | Presentation of Award category 3 - to follow the same process as the first category | MC, Sponsor, Host, Event Manager, Event Coordinator | MC - left lectern, Sponsor/Host - right lectern
2015-05-28 | 19:13 | 19:23 | RS | Presentation of Award category 4 - to follow the same process as the first category | MC, Sponsor, Host, Event Manager, Event Coordinator | MC - left lectern, Sponsor/Host - right lectern
2015-05-28 | 19:15 | 19:15 | RS | Event Coordinator to provide 15min cue to S2 for catering and entertainment to be ready. | Event Coordinator, S2 | Venue
2015-05-28 | 19:23 | 19:29 | RS | Presentation of Award category 5 - to follow the same process as the first category | MC, Host, JW, Event Manager, GS, Event Coordinator | MC - left lectern, Sponsor/Host - right lectern
2015-05-28 | 19:25 | 19:25 | RS | Event Coordinator to give S2 5 minute cue to ensure performer and catering service are on stand-by. | Event Coordinator, S2 | Venue
2015-05-28 | 19:29 | 19:29 |  | MC concludes official proceedings and invites guests to enjoy refreshments and entertainment. MC asks Host and award finalists to proceed to the stage for official photographs. | MC | Stage 1
2015-05-28 | 19:30 | 19:30 | RS | OFFICIAL PROCEEDINGS END
2015-05-28 | 19:30 | 19:30 | RS | COCKTAIL FUNCTION COMMENCES Cocktail function commences (performance and catering). S2 to cue catering and performer to commence. S2 to assist with photographs and handing our certificates. | S2 | Venue
2015-05-28 | 19:30 | 19:30 | BO | S2 to switch off video camera and pack away. | S2 | Venue
2015-05-28 | 19:30 | 19:45 | RS | S9 and S8 available to escort recipients to photo area (behind marquee at Stage 1 end) and coordinate with photographer. S8 to distribute certificates to finalists. Please package trophies and certificates if required, and have available for recipients to pick up on departure. S2 to coordinate photo. | Event Manager, Event Coordinator, S8, S9, S2 | Stage 1 end, behind marquee
2015-05-28 | 19:30 | 19:45 | RS | Available staff to please assist with ushering guests post ceremony if required. | All Staff | Venue
2015-05-28 | 19:30 | 20:15 | RS | Performer #2 performs. S2 to monitor and provide appropriate cues as required. | S2 | Stage 2
2015-05-28 | 19:30 | 20:30 | RS | Catering service. S2 to monitor and provide appropriate cues as required. | S2 | Venue
2015-05-28 | 19:30 | 20:30 | RS | S5 and S6 to manage any media enquiries and liaise with sponsors. Event Manager to stay with Host. | S5, S6 | Venue
2015-05-28 | 19:45 | 19:45 | RS | Host can depart. | Host | Venue
2015-05-28 | 20:00 | 20:00 | RS | S9 and S8 can depart. Return radios and collect belongings from staff room. | S8, S9 | Venue
2015-05-28 | 20:15 | 20:15 | RS | Peformer to finish entertainment set. S2 to assist as required. S2 to cue AV to put on background music for final 15 minutes. | S2 | Stage 2
2015-05-28 | 20:15 | 20:15 | BO | S6 to collect completed photo consent forms from photographer. Photographer can depart. | S6 | Venue
2015-05-28 | 20:25 | 20:25 | RS | S2 to give catering 5 minute cue for end of function. | S2 | Venue
2015-05-28 | 20:30 | 20:30 |  | COCKTAIL FUNCTION CONCLUDES Guests to depart.
2015-05-28 | 20:30 | 20:30 | BO | Event Manager, S5 and S6 can depart. Return radio and collect belongings from staff room. | Event Manager, S5, S6
2015-05-28 | 20:30 | 21:30 | BO | S2 to pack up and bump out. | Event Coordinator, S2
2015-05-28 | 20:45 | 20:45 | BO | AV company to begin packing up and bump out. | AV | Venue
2015-05-28 | 21:30 | 21:30 | BO | Event ends. | All staff
<DATE>
2015-05-29 | 8:00 | 16:00 | BO | Rental company on site to bump out all equipment. | Rental Co | Venue
2015-05-29 | 9:30 | 9:30 | BO | S2 to check in with venue to ensure bump out is running smoothly. | S2 | Office